## Master
Durability Monitoring Timeline | JAN |  |  |  | FEB |  |  |  | MAR |  |  |  | APR |  |  |  | MAY |  |  |  | JUN |  |  |  | JUL |  |  |  | AUG |  |  |  | SEP |  |  |  | OCT |  |  |  | NOV |  |  |  | DEC |  |  |  | Year 2 | [11 empty] | Year 3 | [11 empty] | Year 4
| 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12
Preparatory Activities
Admin/Management
Selection and contracting with research agency | X | X | X | X | X | X
Identification of field team | [10 empty] | X | X | X
Hiring of study coordinator/supervisor etc | X | X | X | X | X | X | X | X
Selection and hiring of mobile data collection consultant | [5 empty] | X | X | X | X
IRB/Ethics Review
Preparation of IRB submission for primary and local IRB | X | X | X
Submission and review by primary IRB |  |  |  | X | X | X | X
Submission and review by local IRB |  |  |  | X | X | X | X | X | X | X | X | X
Responses to IRB questions and final IRB approvals | [12 empty] | X | X | X
Programming mobile data collection system | [12 empty] | X | X | X
ITN mass distribution | [8 empty] | X | X | X | X
First Round of Fieldwork (establish cohort and baseline)
Training preparation - cluster selection, materials | [15 empty] | X | X
Troubleshooting mobile data collection procedures | [15 empty] | X | X
Fieldworker and supervisor training | [17 empty] | X
Fieldwork | [18 empty] | X | X | X
First Round Data Cleaning and Analysis
Data Cleaning | [21 empty] | X
Data Analysis | [22 empty] | X
Report Writing | [23 empty] | X
Dissemination of Report | [24 empty] | X
Submission of dataset to durabilitymonitoring.org | [24 empty] | X
Second Round of Fieldwork (One year after campaign)
Training preparation - cluster selection, materials | [50 empty] | X
Troubleshooting mobile data collection procedures | [50 empty] | X
Fieldworker and supervisor training | [50 empty] | X
Fieldwork | [51 empty] | X
Second Round Data Cleaning and Analysis
Data Cleaning | [52 empty] | X
Data Analysis | [52 empty] | X
Report Writing | [52 empty] | X
Dissemination of Report | [53 empty] | X
Submission of dataset to durabilitymonitoring.org | [53 empty] | X
Third Round of Fieldwork (two years after campaign)
Training preparation - cluster selection, materials | [62 empty] | X
Troubleshooting mobile data collection procedures | [62 empty] | X
Fieldworker and supervisor training | [62 empty] | X
Fieldwork | [63 empty] | X
Third Round Data Cleaning and Analysis
Data Cleaning | [64 empty] | X
Data Analysis | [64 empty] | X
Report Writing | [64 empty] | X
Dissemination of Report | [65 empty] | X
Submission of dataset to durabilitymonitoring.org | [65 empty] | X
Fourth Round of Fieldwork (three years after campaign)
Training preparation - cluster selection, materials | [73 empty] | X
Troubleshooting mobile data collection procedures | [73 empty] | X
Fieldworker and supervisor training | [73 empty] | X
Fieldwork | [74 empty] | X
Fourth Round Data Cleaning and Analysis
Data Cleaning | [75 empty] | X
Data Analysis | [75 empty] | X
Report Writing | [75 empty] | X
Dissemination of Report | [76 empty] | X
Submission of dataset to durabilitymonitoring.org | [76 empty] | X
Final Dissemination
Final results dissemination workshop | [78 empty] | X
Writing up of publishable manuscript(s) | [79 empty] | X | X | X
Peer review and publication | [82 empty] | X | X
Insecticide Content Testing
Baseline insecticide content testing (as part of QAQC process of overall lot) |  |  | x
Endline insecticide content testing | [76 empty] | X
Bio-assays | [20 empty] | X | [32 empty] | X | [11 empty] | X | [10 empty] | X